## SYSTEM PRODUCT BACKLOG
PROJECT PRODUCT BACKLOG |  |  |  | Assignment
UR# | Item | Priority | Status | Team Member | Sprint
1 | Title Page | Low | Closed | Collin James | 1
2 | Table of Contents | Low | Closed | Collin James | 1
3 | Section 1 Executive Summary with Narrative and Conclusions | High | Closed | Collin James | 1
4 | Company Background & Current Environment | Med | Closed | Collin James | 1
5 | Problem Analysis (BPA, BPI, BPR) | Med | Closed | Collin James | 1
6 | Proposed System Objectives and Constraints | Med | Closed | Collin James | 1
7 | Expected Benefits | Low | Closed | Collin James | 1
8 | Context Diagram | Med | Open | Collin James | 2
9 | Section 2 Executive Summary with Narrative and Conclusions | Med | Closed | Collin James | 2
10 | Use Case Diagram | Med | Closed | Collin James | 2 | `
11 | Supplement Specifications (Non-Functional) | High | Closed | Bella Sheprow | 2
12 | Section 3 Executive Summary with Narrative and Conclusions | Med | Closed | Collin James | 3
13 | Complete Data Flow Diagram Package | High | Open | Collin James | 3
14 | Hardware and Software Specification | Med | Closed | Collin James | 3
15 | Navigation Diagram | Med | Open | Collin James | 3
16 | Entity Relationship Diagrams | Med | Open | Collin James | 3
17 | Program Plan showing logic and I/Os (IPO Chart with each program listed) | Med | Closed | Ah'yanna Hart | 3
18 | Standard Naming Conventions | Low | Closed | Bella Sheprow | 3
19 | Section 4 Executive Summary with Narrative and Conclusions
20 | Test Plans
21 | Training Manual and/or Reference/Procedure Manual
22 | Technical Manual
23 | Section 5 Executive Summary with Narrative and Conclusions
24 | Migration Plan (Business, Technical, People Readiness)
25 | Personal Project Assessment (by each member)
26 | Lessons Learned during the project (by group)
27 | Explanation of challenges, problems and discoveries
28 | All Burndown Charts, All Backlogs, All Meeting Logs
29 | Any other supporting documentation
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG |  |  |  | Assignment
# | Item | Priority | Status | Team Member
1 | Title Page | 13 | Completed | Collin James
2 | Table of Contents | 12 | Completed | Collin James
3 | Section 1 Executive Summary with Narrative and Conclusions | 2 | Completed | Collin James
4 | Company Background & Current Environment | 3 | Completed | Collin James
5 | Problem Analysis (BPA, BPI, BPR) | 4 | Completed | Collin James
6 | Proposed System Objectives and Constraints | 5 | Completed | Collin James
7 | Expected Benefits | 6 | Completed | Collin James
8 | Context Diagram | 7 | On-going | Collin James
9 | Use Case Diagram | 9 | On-going | Collin James
10 | Team Contract | 10 | Completed | Josephine Sheprow
11 | Project plan | 11 | On-going | Ah'yanna Hart
12 | Contact Client and discuss | 1 | On-going | Collin James
13 | Website Design | 8 | On-going | Josephine Sheprow

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG |  |  |  | Assignment
# | Item | Priority | Status | Team Member
9 | Section 2 Executive Summary with Narrative and Conclusions | Med | Closed | Collin James
11 | Supplement Specifications (Non-functional Requirements) | High | Closed | Bella Sheprow
12 | Update Use Case Diagram | Med | Closed | Collin James
13 | Update Context Diagram | Med | Closed | Collin James
14 | Site Work | High | Open | Collin James
15 | Update Documentation | Low | Closed | Ah'yanna Hart
16 | Update Team Roles and Charter | Low | Closed | Collin James
17 | Sprint 2 Presentation | Med | Closed | Collin James
18 | Discussions with Client | High | Open | Collin James

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG |  |  |  | Assignment
# | Item | Priority | Status | Team Member
| Section 3 Executive Summary with Narrative and Conclusions | Med | Closed | Collin James
| Complete Data Flow Diagram Package | High | Open | Collin James
| Hardware and Software Specification | Med | Closed | Collin James
| Navigation Diagram | Med | Open | Collin James
| Entity Relationship Diagrams | Med | Open | Collin James
| Program Plan showing logic and I/Os (IPO Chart with each program listed) | Med | Closed | Ah'yanna Hart
| Standard Naming Conventions | Low | Closed | Bella Sheprow
| Create PHP Database using cPanel | Med | Open | Collin James
| Work on About Page | Low | Open | Collin James
| Met with Client | High | Open | Collin James
| Connect mySQL using PHP | High | Open | Collin James

## SPRINT 4 BACKLOG
SPRINT 4 BACKLOG |  |  |  | Assignment
# | Item | Priority | Status | Team Member
Section 4 Executive Summary with Narrative and Conclusions
Test Plans
Training Manual and/or Reference/Procedure Manual
Technical Manual

## SPRINT 5 BACKLOG
SPRINT 5 BACKLOG |  |  |  | Assignment
# | Item | Priority | Status | Team Member

## SPRINT 6 BACKLOG
SPRINT 6 BACKLOG |  |  |  | Assignment
# | Item | Priority | Status | Team Member