## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
| Title Page/Table of Contents | 1 | [14 empty] | Collin James | 12 | bar: Day 5
| Document Backlog | 1 | [14 empty] | Ah'yanna Hart | 4 | bar: Day 5
| Initial Use Case Diagram | 1 | [14 empty] | Bella Sheprow | 4 | bar: Day 7
| Initial Context Diagram | 1 | bar: Day 7
| Initial Product Backlog | 1 | [15 empty] | 20 | Total Team Time | bar: Day 10
| Sprint 1 Backlog | 1 | bar: Day 14
| Sprint 1Burn down Chart | 1 | bar: Day 14
| SCRUM Meeting Log | 1 | bar: Day 14
| Team Roles and Team Charter | 1 | bar: Day 11
| Project Plan | 1 | bar: Day 14
| Start and Design Website | 3 | bar: Day 4; Day 8 to Day 9
| Work with Client | 4 | bar: Day 3; Day 5 to Day 6; Day 11
Remaining Effort |  | 17 | 17 | 17 | 16 | 15 | 12 | 11 | 9 | 8 | 7 | 6 | 4 | 4 | 4 | 0
Ideal Effort |  | 17 | 15.7857 | 14.5714 | 13.3571 | 12.1429 | 10.9286 | 9.7143 | 8.5 | 7.2857 | 6.0714 | 4.8571 | 3.6429 | 2.4286 | 1.2143 | 4.885e-15

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
| Sprint 2 Executive Summary | 1 | [14 empty] | Collin James | 9 | bar: Day 14
| Update Context Diagram | 0.5 | [14 empty] | Ah'yanna Hart | 4 | bar: Day 5
| Update Use Case Diagram | 0.5 | [14 empty] | Bella Sheprow | 4 | bar: Day 5
| Supplement Specifications (Non-functional Requirements) | 1 | [14 empty] | 0 | bar: Day 14
| Work on Site | 4 | Day 9: 1; Day 13: 2; Day 14: 1 |  | 17 | Total Team Time
| Update Documentation | 1 | bar: Day 13
| Sprint 2 Presentation | 1 | bar: Day 13
| Update Team Roles and Charter | 0.5 | bar: Day 13
| Work with Client | 4 | bar: Day 7 to Day 8; Day 11 to Day 12
| Meetings | 2 | bar: Day 9; Day 14
Remaining Effort |  | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 14.5 | 14.5 | 13.5 | 12.5 | 10.5 | 10.5 | 9.5 | 8.5 | 3.5 | -0.5
Ideal Effort |  | 16.5 | 15.3214 | 14.1429 | 12.9643 | 11.7857 | 10.6071 | 9.4286 | 8.25 | 7.0714 | 5.8929 | 4.7143 | 3.5357 | 2.3571 | 1.1786 | -3.1086e-15

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
| Executive Summary | 0.5 | Day 3: 0.5 | Collin James | 12.5
| Complete Data Flow Diagram Package | 3 | [14 empty] | Ah'yanna Hart | 3.5 | bar: Day 12 to Day 14
| Hardware and Software Specification | 1 | [14 empty] | Bella Sheprow | 3.5 | bar: Day 2
| Navigation Diagram | 1 | bar: Day 1
| ERD | 1 | [15 empty] | 19.5 | Total Team Time | bar: Day 13
| IPO Chart | 1 | bar: Day 2
| Standard Naming Conventions | 1 | bar: Day 14
| Create PHP Database using cPanel | 2 | bar: Day 12 to Day 13
| Work on About Page | 1 | bar: Day 14
| Met with Client | 3 | bar: Day 4 to Day 5; Day 11
| Connect mySQL using PHP | 2 | bar: Day 12; Day 14
| Meetings with Group | 3 | Day 2: 1; Day 14: 2
Remaining Effort |  | 19.5 | 18.5 | 15.5 | 15 | 14 | 13 | 13 | 13 | 13 | 13 | 13 | 12 | 9 | 6 | 0
Ideal Effort |  | 19.5 | 18.1071 | 16.7143 | 15.3214 | 13.9286 | 12.5357 | 11.1429 | 9.75 | 8.3571 | 6.9643 | 5.5714 | 4.1786 | 2.7857 | 1.3929 | 5.7732e-15

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Collin James
Ah'yanna Hart
Bella Sheprow
0
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Collin James
Ah'yanna Hart
Bella Sheprow
0
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Collin James
Ah'yanna Hart
Bella Sheprow
0
[18 empty] | 0 | Total Team Time
Total Project Time
[18 empty] | Sprint 1 | 20
[18 empty] | Sprint 2 | 17
[18 empty] | Sprint 3 | 19.5
[18 empty] | Sprint 4 | 0
[18 empty] | Sprint 5 | 0
[18 empty] | Sprint 6 | 0
[19 empty] | 56.5 | Total Project Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0